## Plan
Phase | Task | Owner Role | Duration (days) | Dependencies | Deliverable
0 - Readiness | Define success criteria and KPIs | Sponsor | 2 |  | Project charter
0 - Readiness | Confirm scope and modules | Project Manager | 2 |  | Scope baseline
1 - Foundation | Establish SSO and identity mappings | IT Admin | 3 | Project charter | SSO live
1 - Foundation | Configure chart of accounts and tax settings | Finance Lead | 5 | Scope baseline | Finance baseline configured
1 - Foundation | Set up roles and permissions | Security Lead | 3 | SSO live | RBAC framework
2 - Integrations | Connect data sources via API and webhooks | Integration Engineer | 7 | Foundation complete | Data flows live
2 - Integrations | Migrate master data to ACME Horizon | Data Lead | 5 | RBAC framework | Master data loaded
2 - Integrations | Enable Apex Analytics dashboards | Analytics Lead | 4 | Data flows live | Baseline dashboards
3 - UAT and Launch | User acceptance testing | Project Manager | 7 | Integrations complete | Signed UAT
3 - UAT and Launch | Cutover rehearsal and go-live checklist | Project Manager | 3 | Signed UAT | Go-live checklist
3 - UAT and Launch | Hypercare and stabilization | Support Lead | 14 | Go-live | Stabilization report